## Sheet1
Number | Task | Category | Owner | Current Status | Steps required | Expected Finish Date | Target Week | WeeklyTarget | Actual Finish Date
1 | LBA/LBO/LE | ADR | Raymond | Not Start | 1. Review with PM 2. Review with AR Dev team 3. Review with Fintech team 4. Create/update the ADR | 2012-03-18 |  | 1. Get into the ADR
2 | CM Data Model changes Design | DB | Tony | In Progress | According to current LDM/DB Model, generate the design for CM Data Model | 2012-02-09
3 | CM Data Model changes | DB | Jason | In Progress | 1. Send Dev committee for review 2. Log CR Request 3. Get to the CDRM DB & Various DB 4. Prepare DBSchema project after LBA is ready | 2012-03-02 |  | 1. Get the Data model reviewed and log the CR request
4 | bootstrap data(lookup/seed data) | DB | Jason | Not Start | 1. Review the seed data TDD 2. prepare the script for anything additional need to be add. 3. Log bug to get into the CDRM DB (ar/db/data)(ar/db/noship) | 2012-03-02 |  | 1. Get the script ready and log the bug
5 | PL/SQL Package Design | DB | Tony & Jason | Not Start | According to current FDD Solution, generate PL/SQL definition(package name/procedure name) | 2012-03-02
6 | CC PLSQL code | DB | Tony & Jason | Not Start | 1. Review with the AR dev team. 2. Code in DB Schema Project | 2012-03-16 |  | 1. Get the PLSQL transaction ready and reviewed. 2. Extensively testing required on common impacted code.
7 | CC Service Project | Service | Tony | Not Start | 1. Junit testing/Jaudit 2. Review DTC/TDD 3. Code review 4. Prepare the project | 2012-03-23
8 | CC Service Testing Project | Testing | Tony | Not Start | 1. Junit testing/Jaudit 2. Review DTC/TDD 3. Code review 4. Prepare the project | 2012-03-23
9 | CC Ess Project | Ess | Jason | Not Start | 1. Create Ess Project 2. Review with AR Dev Team 3. Merge into ADE | 2012-03-23
10 | CC Ess Harness Test Project | Testing | Jason | Not Start | 1. Create Ess harness Test Project 2. Review with AR Dev Team 3. Prepare Project | 2012-03-23
11 | Update Existing Ess Code | Ess |  | Not Start | 1. Update Existing code to merge credit checking 2. Review with AR Dev Team 3. Prepare Project | 2012-03-23
12 | SetUp UI | Model/Ui Project |  | Not Start | 1. Update Existing code to merge Customer Account/Customer Profile Class code. 2. Review with AR Dev Team 3. Prepare Project | 2012-03-30
13 | TDD generation |  | All | Not Start |  | 2012-03-30
14 | DTC | Testing | All | Not Start |  | 2012-03-30
15 | Local Deployment Integration Test | Testing | All | Not Start |  | 2012-03-30
16 | BPM/Security Spreadsheet | Security |  | Not Start | 1. Review with PM 2. Review with AR Dev team 3. Review with Fintech team 4. Create the ADR
17 | Security Artifacts | Security |  | Not Start | 1. Review with Jazn file changes 2. Review the data security changes 3. Prepare the data security artifacts 4. add to ADE (ar/db/data)(ar/db/noship)
18 | Message respository | Seed |  | Not Start | 1. Dev prepare the message list with detailed information 2. PM/Doc to review 3. PM enter the message in MRT 4. Dev download the message data and add to ADE
19 | String respository/Resource project | Seed |  | Not Start | 1. PM to come up the string list 2. Dev to review 3. Doc to review and approve 4. PM to enter to the string repository 5. Incorporate resource project into the code

## PLSQL Plan
Package Name | Procedure/Function Name | Owner | Target | Comment | Developer Comment
ARP_CC_AVAIL_CREDIT_PKG | All procedures | Tonny | 2012-Mar-13 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
ARP_CC_AUTH_PKG | All procedures | Jason | 2012-Mar-13 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
AR_CM_UTILITY_PKG | All procedures | Tonny | 2012-Mar-14 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
AR_CM_CC_LIB_PVT | PROCESS_EXPIRED_AUTHORIZATION | Jason | 2012-Mar-14 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
AR_CM_CC_CORE_PKG | UPDATE_AVAILABLE_CREDIT | Tonny | 2012-Mar-15 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
AR_CM_CC_CORE_PKG | CONVERT_AVAILABLE_CREDIT_TO_REQUEST_CURRENCY | Jason | 2012-Mar-15 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
AR_CM_CC_CORE_PKG | CHECK_REQUEST_AMOUNT_WITH_AVAILABLE_CREDIT | Tonny | 2012-Mar-16 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
AR_CM_CC_CORE_PKG | CALCULATE_EXPIRATION_DATE | Jason | 2012-Mar-16 | Before running code, please use utPL/SQL to write the Unit Test first | Done for the package code and utPL/SQL.
AR_CM_CC_LIB_PVT | PROCESS_DE_AUTHORIZATION | Tonny | 2012-Mar-19 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_LIB_PVT | PROCESS_AUTHORIZATION | Jason | 2012-Mar-19 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_LIB_PVT | PROCESS_RE_AUTHORIZATION | Tonny | 2012-Mar-20 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_LIB_PVT | PROCESS_PRE_AUTHORIZATION | Jason | 2012-Mar-20 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_LIB_PVT | PROCESS_EXCLUDE_EXPIRATION_FLAG | Tonny | 2012-Mar-21 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_VAL_PVT | Validate | Tonny | 2012-Mar-21 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_VAL_PVT | VALIDATE_ACCOUNT_PROFILE | Jason | 2012-Mar-21 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_VAL_PVT | Validate_Required | Tonny | 2012-Mar-22 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_VAL_PVT | Validate_Request_Type | Jason | 2012-Mar-22 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_VAL_PVT | Validate_Business_Rule | Tonny | 2012-Mar-23 | Before running code, please use utPL/SQL to write the Unit Test first
AR_CM_CC_API_PUB | All Procedures/Functions | Jason | 2012-Mar-23 | Before running code, please use utPL/SQL to write the Unit Test first